## Sheet1
Task | Start Time | End Time | Status
Obj Loader - refactoring ply | 2011-06-09 | 2011-11-09
GUI - basic interface | 2011-01-09 | 2011-06-09 | In Progress
Glossy Sampling - correct pdf(populate ds) | 2011-12-09 | 17/9/2011
GUI - Lights - depend on designer | 2011-06-09 | 17/9/2011
Fresnel | 18/9/2011 | 24/9/2011
Specular BRDF, PhongBRDFs, Sampling Phong | 25/9/2011 | 2011-02-10
GUI - Shapes - depend on designer | 18/9/2011 | 2011-02-10
MIS | 2011-03-10 | 2011-09-10
Ward, NewWard, Sampling Ward, NewWard | 2011-10-10 | 17/10/2011
Interpolate Normal, uv-Triangle, Ply Loadr, Obj | 18/10/2011 | 25/10/2011
GUI - Material - depend on designer | 2010-03-10 | 25/10/2011
Introduction Texture(Utility Classes) | 26/10/2011 | 31/10/2011
Triangle, Sphere, Rectangle texturing | 2011-01-11 | 2011-08-11
Procedural Texture - Just Basic | 2011-09-11 | 15/11/2011
GUI - ??
BTDF - basic glass - Basic Transsmision BRDF | 16/11/2011 | 22/11/2011
Rough Glass - paper 2007 - Sampling | 23/11/2011 | 30/11/2011
Multi Threading - Tdasm | 2011-01-12 | 2011-05-12
Multi Threading - Multiple Runtime | 2011-06-12 | 15/12/2011
Distribution | 16/12/2011 | 22/12/2011
Release ALPHA VRESION 0.1
Side Task - If time allowed
Preparation for Volume Rendering
Preparation for Spectral Rendering